## Overview
Vedha — Project Tracker
Autonomous security-testing platform. End-to-end task tracker derived from the backend roadmap, strategy, and team playbook.
Generated 2026-10-16. Single source of truth = 'Master Task List'. Fill Owner and Status columns there.
How to use this workbook
1. Master Task List: every task with description, files, deliverable, verification, dependencies, effort. Edit Owner + Status here.
2. Phase Plan: the five delivery phases and which tasks belong to each; use for sprint planning.
3. Team Roster: the eight teams, their focus, and cross-team dependencies.
4. Status and priority cells have dropdowns. The summaries below recalc automatically from the Master Task List.
Status summary |  | Priority summary
Status | Count | Priority | Count | Meaning
Not Started | 55 | P0 | 12 | Safety-critical / pre-real-world
In Progress | 0 | P1 | 29 | Robustness & reliability
Blocked | 0 | P2 | 12 | Scale & quality
In Review | 0 | - | 3 | Shared setup
Done | 1
Total | 56 | Percent complete | 1.786%

## Master Task List
Task ID | Team | Phase | Priority | Title | Description / What to build | Key files | Deliverable | Verification / Acceptance | Dependencies | Effort | Owner | Status | Notes
T0.1 | Shared | P0: Foundations | - | Create root CLAUDE.md | Add shared conventions + architecture map so every Claude Code session picks it up automatically. | CLAUDE.md | CLAUDE.md in repo root | File exists; a fresh Claude Code session cites the build/test commands and conventions. |  | S |  | Done
T0.2 | Shared | P0: Foundations | - | Agree integration branch & migration order | Leads agree the integration branch name and a global ordering/numbering for DB migrations to avoid collisions. | docs/ | Written agreement in docs/ | A single documented migration order exists; Teams 1/4/5 reference it. |  | S |  | Not Started
T0.3 | Shared | P0: Foundations | - | Config-flag convention | Agree the VEDHA_ flag naming and safe-default rule; add a short section to config docs. | backend/pkg/config/config.go | Documented convention | All new runtime-behavior flags use VEDHA_ prefix with a safe default. |  | S |  | Not Started
T1.1 | 1 Safety & Policy | P0: Safety Floor | P0 | Scope engine core package | New package with Scope type (allowed CIDRs, domains w/ wildcards, ports, deny list, time window) and Check(target). | backend/pkg/tools/scope/ | scope package + table-driven tests | go test ./pkg/tools/scope/ passes; cases cover IPv4/IPv6 CIDR, wildcard domains, deny precedence, ports, malformed input. |  | M |  | Not Started
T1.2 | 1 Safety & Policy | P0: Safety Floor | P0 | Enforce scope at tool boundary | Intercept terminal/pentester/browser calls, extract target, call Check; deny out-of-scope. Behind VEDHA_SCOPE_ENFORCEMENT (default off). | backend/pkg/tools/executor.go, terminal.go, browser.go | Enforcement wired behind flag | With flag on and single-host scope, an out-of-scope target returns a deny string and the handler is never called (test double asserts). | T1.1 | M |  | Not Started
T1.3 | 1 Safety & Policy | P0: Safety Floor | P0 | Budgets & kill-switch | Per-flow caps on cost(USD), iterations, wall-clock. Accumulate each loop; stop flow when a non-zero cap is exceeded. | backend/pkg/providers/performer.go, controller/flow.go, config.go | Budget enforcement + tests | With a tiny VEDHA_MAX_FLOW_ITERATIONS the flow stops at the cap; defaults leave behavior unchanged. |  | M |  | Not Started
T1.4 | 1 Safety & Policy | P3: Product & Trust | P1 | Human-approval gate | Gate high-impact actions (confirmed exploitation, credential use, destructive cmds) via the existing ask tool. | backend/pkg/tools/executor.go, tools.go | Approval gate behind flag | A flagged high-impact action pauses for approval and does not execute until approved (test). | T1.2 | M |  | Not Started
T1.5 | 1 Safety & Policy | P0: Safety Floor | P0 | Scope schema: migration + API inputs | Add scope JSON column on flows; extend GraphQL/REST create-flow inputs to accept a scope. | backend/migrations/sql/, backend/pkg/graph/, server/ | Migration + API field | Migration applies up/down; a flow can be created with a scope via API and it persists. | T1.1,T0.2 | M |  | Not Started
T1.6 | 1 Safety & Policy | P0: Safety Floor | P0 | Policy docs + target-parsing threat model | Document policy format; threat-model the target extraction so obfuscated commands cannot evade the check (deny-on-uncertainty). | docs/ | Doc + threat model | Security reviewer signs off; ambiguous targets default to deny in tests. | T1.2 | S |  | Not Started
T2.1 | 2 Sandbox & Infra | P0: Safety Floor | P0 | Container capability hardening | Drop all caps, add back NET_RAW always + NET_ADMIN only when enabled; set no-new-privileges, seccomp. | backend/pkg/docker/client.go | Hardened container create | nmap SYN scan still works; capsh --print shows reduced caps; existing toolchain unaffected. |  | M |  | Not Started
T2.2 | 2 Sandbox & Infra | P0: Safety Floor | P0 | Sandbox resource limits | Set Memory, NanoCPUs, PidsLimit from VEDHA_SANDBOX_* config. | backend/pkg/docker/client.go, config.go | Resource limits applied | A fork bomb / memory hog in the sandbox is bounded; limits visible via docker inspect. |  | S |  | Not Started
T2.3 | 2 Sandbox & Infra | P0: Safety Floor | P0 | Remove/proxy host Docker socket | Eliminate raw /var/run/docker.sock mount under DOCKER_INSIDE, or replace with a restricted socket proxy. | backend/pkg/docker/client.go | Decision + implementation | No raw host socket is exposed to agent-run code; decision documented. |  | M |  | Not Started
T2.4 | 2 Sandbox & Infra | P1: Reliability | P1 | Terminal: honest timeout ceiling | Honor documented 1200s ceiling instead of silently clamping >20min down to 5min. | backend/pkg/tools/terminal.go | Fixed timeout logic + tests | A 30-min timeout runs 30 min; clamp logic unit-tested. |  | S |  | Not Started
T2.5 | 2 Sandbox & Infra | P1: Reliability | P1 | Terminal: trackable detached execs | Registry of background executions keyed by id so output is retrievable and they are cancellable. | backend/pkg/tools/terminal.go | Detach registry + tests | A detached command's output can be fetched later and the job cancelled. |  | M |  | Not Started
T2.6 | 2 Sandbox & Infra | P1: Reliability | P1 | Terminal: surface exit codes | Read exit code from ContainerExecInspect and include it in results. | backend/pkg/tools/terminal.go | Exit code in result + tests | A failing command reports non-zero; empty output no longer masquerades as success. |  | S |  | Not Started
T2.7 | 2 Sandbox & Infra | P0: Foundations | P1 | Azure IaC (Bicep) | Bicep modules: AKS/Container Apps, session pool, Postgres+pgvector, AI Search, Key Vault, Entra app, VNet+NSG+Firewall, Front Door+WAF. | deploy/ | Validated Bicep + README | az bicep build succeeds with no errors; README documents deploy commands. |  | L |  | Not Started
T2.8 | 2 Sandbox & Infra | P3: Product & Trust | P1 | Azure Container Apps sandbox adapter | Adapter so tool execution can target ACA Dynamic Sessions/Sandboxes (microVM) instead of raw Docker. | backend/pkg/docker/ (interface), new adapter | Pluggable sandbox backend | Same tool run succeeds against the ACA backend in staging; Docker backend still works. | T2.7 | L |  | Not Started
T2.9 | 2 Sandbox & Infra | P0: Safety Floor | P0 | Network egress enforcement | Default-deny outbound; allow only in-scope targets + required infra via NSG/Azure Firewall / local nftables sidecar. | backend/pkg/docker/client.go, deploy/ | Egress policy aligned to scope | Out-of-scope egress from the sandbox is blocked at the network, mirroring T1.1 allowlist. | T1.1,T2.7 | L |  | Not Started
T2.10 | 2 Sandbox & Infra | P4: Scale & GA | P2 | Sandbox fleet runbook | Operational runbook for provisioning, scaling, and tearing down sandboxes. | docs/ | Runbook | On-call can follow the runbook to operate the fleet. | T2.8 | S |  | Not Started
T3.1 | 3 Providers & Models | P1: Reliability | P1 | Per-role model config update | Set best-fit model per tier across anthropic/openai/gemini configs (deep/orchestration/cheap). | backend/pkg/providers/*/config.yml | Updated role->model maps | Configs load/validate; testAgent passes for each role with staging keys. |  | M |  | Not Started
T3.2 | 3 Providers & Models | P1: Reliability | P1 | Bedrock tiering + reasoning | Replace single-model-for-all with real tiering; add reasoning blocks for thinking-capable models. | backend/pkg/providers/bedrock/config.yml | Tiered Bedrock config | Bedrock roles use tier-appropriate models; reasoning blocks present; tests pass. | T3.1 | S |  | Not Started
T3.3 | 3 Providers & Models | P1: Reliability | P1 | Reconcile default-model constants | Align hardcoded Go default model constants with the YAML so they don't silently diverge. | backend/pkg/providers/*/*.go | Consistent defaults | Grep shows Go defaults match a real role model; no orphan defaults (e.g. gemini-2.5-flash). | T3.1 | S |  | Not Started
T3.4 | 3 Providers & Models | P1: Reliability | P1 | Model fallback & failover | Ordered fallback models (+ optional fallback provider) tried on retryable/capacity failure before abort. Flag VEDHA_MODEL_FALLBACK. | backend/pkg/providers/provider/wrapper.go, performer.go, pconfig | Fallback chain + tests | Fake primary returns 429 past budget -> task completes on fallback model. |  | M |  | Not Started
T3.5 | 3 Providers & Models | P1: Reliability | P1 | Token-aware context management | Per-model context-window table + token counting drives summarization; byte caps become fallback for unknown models. | backend/pkg/providers/provider.go, csum/ | Token-aware limits + tests | A long chat stays under the model's real window; no overflow; unknown model falls back to byte caps. |  | L |  | Not Started
T3.6 | 3 Providers & Models | P1: Reliability | P1 | Proactive rate limiting + jittered backoff | Client-side concurrency/token-rate limiter per provider; jittered exponential backoff; robust 429 detection. | backend/pkg/providers/provider/wrapper.go | Limiter + backoff + tests | Parallel sub-agents do not burst past provider limits in a load test; backoff has jitter. |  | M |  | Not Started
T3.7 | 3 Providers & Models | P1: Reliability | P1 | Embedding upgrade + version guard | Default to text-embedding-3-large (configurable); tag vectors with embedding-model version; refuse mixed-model search. | backend/pkg/providers/embeddings/embedder.go | Upgrade + version guard | Switching models surfaces the version guard, not silent bad matches; guard unit-tested. |  | M |  | Not Started
T3.8 | 3 Providers & Models | P2: Scale & Quality | P2 | Single source of truth for prices | Reconcile config.yml vs models.yml prices; document the update process. | backend/pkg/providers/*/config.yml, models.yml | Reconciled prices + doc | No price disagreements between the two files; cost accounting matches provider pricing. | T3.1 | S |  | Not Started
T4.1 | 4 Memory & Data | P0: Foundations | P0 | Typed findings & evidence model | Migration for findings + evidence tables; sqlc queries; Go model following existing patterns. | backend/migrations/sql/, sqlc/models/, pkg/database/ | Findings schema + queries | Migration up/down clean; a finding round-trips with all typed fields; query tests pass. | T0.2 | L |  | Not Started
T4.2 | 4 Memory & Data | P1: Reliability | P1 | report_finding barrier tool | New validated barrier tool for agents to record a typed finding. | backend/pkg/tools/ | report_finding tool | Agent records a finding via the tool; schema validation rejects malformed findings. | T4.1 | M |  | Not Started
T4.3 | 4 Memory & Data | P2: Scale & Quality | P1 | Managed pgvector schema | Bring embedding table under migration control with pinned dimension + HNSW index. | backend/migrations/sql/ | Managed vector schema | Migration applies; similarity queries use the HNSW index (check query plan). |  | M |  | Not Started
T4.4 | 4 Memory & Data | P2: Scale & Quality | P1 | RAG reranking | Reranking after similarity search behind VEDHA_RERANK; local + Azure AI Search implementations. | backend/pkg/tools/memory.go | Reranker interface + 2 impls | With rerank on, results return in reranker order; fake-reranker test asserts reorder. |  | M |  | Not Started
T4.5 | 4 Memory & Data | P3: Product & Trust | P2 | Attack-path graph schema | Unified graph (assets, creds, findings, relationships) on Graphiti/Neo4j spanning web+network+cloud. | backend/pkg/graphiti/, templates/graphiti/ | Graph schema + writers | A web foothold and a network finding link in one graph; traversal returns the chain. | T4.1 | L |  | Not Started
T4.6 | 4 Memory & Data | P2: Scale & Quality | P2 | Log retention & partitioning | Time-based partitioning + retention for termlogs/msglogs/toolcalls. | backend/migrations/sql/ | Partitioning + retention | Old rows age out per policy; high-volume tables partitioned; no unbounded growth. |  | M |  | Not Started
T4.7 | 4 Memory & Data | P1: Reliability | P1 | Re-embedding migration | Migration/tooling to re-embed stored vectors when the embedding model changes. | backend/migrations/sql/, tooling | Re-embedding path | Running it re-embeds existing content under the new model and updates version tags. | T3.7,T4.3 | M |  | Not Started
T4.8 | 4 Memory & Data | P0: Foundations | P1 | Findings taxonomy | Define vulnerability classes, severity scale, CVSS usage with security input. | docs/ | Taxonomy doc | Taxonomy agreed and referenced by T4.1 schema enums. |  | S |  | Not Started
T5.1 | 5 Platform & Identity | P0: Foundations | P0 | Authorization characterization tests | Tests locking in current GraphQL/permission authz behavior before changing it. | backend/pkg/graph/context.go, server/auth/permissions.go | Authz test suite | Tests cover cross-user denial, admin bypass, *.admin regex, missing-perm denial; all pass on current code. |  | M |  | Not Started
T5.2 | 5 Platform & Identity | P3: Product & Trust | P1 | Entra ID OIDC provider | Add Microsoft Entra ID OIDC alongside Google/GitHub; map Entra groups to roles. Gated by OAUTH_ENTRA_*. | backend/pkg/server/oauth/ | Entra provider + tests | An Entra login creates/links a user with the mapped role; existing providers unaffected. | T5.1 | M |  | Not Started
T5.3 | 5 Platform & Identity | P3: Product & Trust | P2 | SAML seam | Clean extension point for SAML on top of the OIDC work. | backend/pkg/server/oauth/, auth/ | SAML interface seam | SAML can be added without reworking the auth flow; seam documented. | T5.2 | S |  | Not Started
T5.4 | 5 Platform & Identity | P3: Product & Trust | P1 | Tenancy & isolation | tenants table + tenant_id on users/flows; enforce isolation in ownership checks; default single tenant. | backend/migrations/sql/, pkg/graph/context.go | Tenancy + isolation | User in tenant A cannot see tenant B flows (test); existing installs migrate to one tenant. | T5.1,T0.2 | L |  | Not Started
T5.5 | 5 Platform & Identity | P3: Product & Trust | P1 | Audit log | Append-only audit_log table; record flow create/delete, provider/prompt changes, logins, token use. | backend/migrations/sql/, new audit package | Audit log + recording | Each audited action produces exactly one row with actor/action/target (tests). | T0.2 | M |  | Not Started
T5.6 | 5 Platform & Identity | P3: Product & Trust | P2 | Super-admin & data migration | Define super-admin model; plan+implement data migration for existing single-tenant installs. | backend/migrations/sql/, docs/ | Super-admin + migration | Super-admin crosses tenants by design; existing data migrates cleanly. | T5.4 | S |  | Not Started
T6.1 | 6 Reporting & Integrations | P3: Product & Trust | P1 | Reporter from typed findings | Build reports (structured JSON + PDF) from the findings table instead of free text. Old path behind a flag during transition. | backend/pkg/templates/prompts/reporter.tmpl, reporter path | New reporter + tests | A report from fixture findings contains every finding with evidence + confidence. | T4.1 | M |  | Not Started
T6.2 | 6 Reporting & Integrations | P3: Product & Trust | P1 | Verified proof-of-exploit | Attach exact command chain + captured evidence + confidence score to each finding. | findings package, reporter | Proof attached to findings | 'Verified' label only applied when exploitation actually succeeded (security review). | T4.1,T6.1 | M |  | Not Started
T6.3 | 6 Reporting & Integrations | P3: Product & Trust | P1 | Run-to-run diffing | Stable finding fingerprint; compute new/fixed/still-open across runs; expose via API + reports. | findings package, API | Diff engine + tests | Two runs (one fixed, one new) report exactly one fixed and one new. | T4.1 | M |  | Not Started
T6.4 | 6 Reporting & Integrations | P3: Product & Trust | P1 | Integrations framework + Jira + webhook | Common PushFinding/PushReport interface; Jira + signed generic webhook first; per-tenant config. | backend/pkg/integrations/ | Framework + 2 integrations | Each posts expected payload to an httptest server; no live calls in CI. | T4.1 | M |  | Not Started
T6.5 | 6 Reporting & Integrations | P4: Scale & GA | P2 | DefectDojo + Slack integrations | Add DefectDojo and Slack on the integrations framework. | backend/pkg/integrations/ | 2 more integrations | httptest assertions for each; per-tenant config respected. | T6.4 | M |  | Not Started
T6.6 | 6 Reporting & Integrations | P4: Scale & GA | P2 | Integration docs + verified-label review | Customer-facing setup/field-mapping docs; security review of the verified label semantics. | docs/ | Docs + sign-off | Docs cover each integration; reviewer confirms verified semantics. | T6.4,T6.2 | S |  | Not Started
T7.1 | 7 Eval & QA | P0: Foundations | P1 | Evaluation harness | cmd/eval runs Vedha vs known-vulnerable targets, compares to ground truth, outputs detection rate, FP rate, cost, time (JSON). | backend/cmd/eval/ (or eval/) | Eval harness + 1 target | Produces a JSON report with the four metrics against at least one real vulnerable target. |  | L |  | Not Started
T7.2 | 7 Eval & QA | P4: Scale & GA | P2 | Grow benchmark corpus | Add targets + ground truth; publish methodology (also a marketing asset). | eval/ | Expanded corpus | Corpus covers multiple vuln classes; methodology published. | T7.1 | M |  | Not Started
T7.3 | 7 Eval & QA | P0: Foundations | P1 | Controller lifecycle tests | Unit tests for flow lifecycle (create, status transitions, stop, finish) using fakes. | backend/pkg/controller/ | Controller tests | Coverage of the flow lifecycle rises from ~0 to an agreed floor (e.g. 50%). |  | L |  | Not Started
T7.4 | 7 Eval & QA | P1: Reliability | P1 | Agent loop tests | Tests for agent loop stop conditions and retry paths with provider/db fakes. | backend/pkg/providers/performer.go | Agent loop tests | Stop conditions and retries covered; no production logic changed silently. |  | M |  | Not Started
T7.5 | 7 Eval & QA | P2: Scale & Quality | P2 | Docker client tests | Tests for container provisioning/lifecycle with a fake docker client. | backend/pkg/docker/ | Docker tests | Create/hardening/limits/teardown covered against a fake client. | T2.1,T2.2 | M |  | Not Started
T7.6 | 7 Eval & QA | P2: Scale & Quality | P2 | Memory path tests | Tests for the RAG store/retrieve path with a fake vector store. | backend/pkg/tools/memory.go | Memory tests | Store, retrieve, flow-scoping, and fallback filters covered. |  | M |  | Not Started
T7.7 | 7 Eval & QA | P0: Foundations | P0 | CI PR workflow | GitHub Actions: build, vet, gofmt, golangci-lint, test -race; required on PRs; Go build cache. | .github/workflows/ | Required PR workflow | Fails on a deliberately broken build; passes clean; marked required. |  | M |  | Not Started
T7.8 | 7 Eval & QA | P3: Product & Trust | P2 | Nightly eval workflow | Nightly run of the eval harness against the corpus; upload JSON report as artifact. | .github/workflows/ | Nightly eval job | Nightly run produces and uploads the metrics report. | T7.1,T7.7 | S |  | Not Started
T7.9 | 7 Eval & QA | P0: Foundations | P1 | Own CLAUDE.md + quality gates | Maintain canonical CLAUDE.md; set and enforce coverage + lint gates in CI. | CLAUDE.md, .github/workflows/ | Gates enforced | CI enforces lint + coverage floor; CLAUDE.md kept current. | T0.1,T7.7 | S |  | Not Started

## Phase Plan
Delivery Phases
Sequencing for ~9-12 months to enterprise GA with a 3-8 person senior team. Durations are planning ballparks, not commitments.
Phase | Duration (ballpark) | Team size | Goal | Exit / success target | Task count
P0: Foundations | ~1 month | 2-3 | Provider abstraction, sandbox skeleton, safety-layer + findings-model + eval scaffolding, CI. | One agent runs one safe, scoped, evidenced finding end to end. | 11
P0: Safety Floor | within month 1-2 | 3-5 | Scope engine, egress, hardening, resource limits, budgets, socket, secrets. | Nothing runs against a real network until this lands. | 9
P1: Reliability | 2-3 months | 3-6 | Model upgrade + fallback, token-aware context, terminal fixes, rate limiting, embeddings. | Long autonomous runs survive provider blips; correct exit/timeout semantics. | 13
P2: Scale & Quality | parallel + 2-3 months | 4-6 | Vector schema, reranking, retention, Docker/memory tests, price reconciliation. | Managed data layer; risky core under test. | 6
P3: Product & Trust | 3-4 months | 5-8 | Findings/reporting, verified proof, diffing, Entra SSO, tenancy, audit, integrations, attack graph, ACA sandbox. | Pass a design partner security review; measurable FP rate. | 13
P4: Scale & GA | ongoing | 8+ | Benchmark corpus, more integrations, runbooks, docs, managed cloud tier. | Paying customers, SLA, continuous engagements at scale. | 4

## Team Roster
Teams & Dependencies
Eight workstreams. Each team owns its section of the playbook (docs/VEDHA_TEAM_PLAYBOOK.md).
Team | Focus | Key packages | Depends on | Blocks | Task count
Shared | Setup, conventions, migration ordering | CLAUDE.md, config | - | All teams | 3
1 Safety & Policy | Scope engine, budgets, approval gates | pkg/tools/scope, executor | Shared | Team 2 egress | 6
2 Sandbox & Infra | Container hardening, terminal, Azure IaC | pkg/docker, pkg/tools/terminal, deploy | Team 1 (scope) | Team 7 docker tests | 10
3 Providers & Models | Models, fallback, context, embeddings | pkg/providers | - | Team 4 (embeddings) | 8
4 Memory & Data | Findings model, vector schema, graph | migrations, sqlc, pkg/graphiti | Shared | Teams 6,7 | 8
5 Platform & Identity | SSO, tenancy, audit, authz tests | pkg/server, pkg/graph | Shared | - | 6
6 Reporting & Integrations | Reports, proof, diffing, connectors | reporter, pkg/integrations | Team 4 | - | 6
7 Eval & QA | Eval harness, core tests, CI | cmd/eval, .github/workflows | Team 4 (ground truth) | All (gates) | 9